## excel(14)
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 30.2 | 8.35 | 37
Planned Time | 0.11319 |  | 1899-12-31 12:07
Actual Tiempo |  | 0.15972 | 1900-01-01 02:27
CPI (Cost-Performance Index) |  |  | 0.72
% Reuse | 0% | 0% | 0%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 8.18 | 0 | 8.04
Total Defects/KLOC or equivalent | 16.4 | 31.2 | 16.6
Yield % | 51.7% | 100% | 53.3%
Code Review Rate | 1190 | 120 | 1286
% Appraisal COQ | 4.04% | 11.7% | 4.63%
% Failure COQ | 13.5% | 4.35% | 12.8%
COQ A/F Ratio | 0.3 | 2.7 | 0.36
PQI | 0 | 0.06 | 0.01
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:03 PM el 18/04/2017