## excel-4
/Non Project/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 2.19 | 5.45 | 3.4
Defects/Hour - Code Review | 1.3 | 0 | 1.38
Defects/Hour - Compile | 0 | 0 | 0
Defects/Hour - Test | 1.89 | 0 | 2.41
DRL (DLDR/UT) | 1.16 | 2.26 | 1.41
DRL (Code Review/UT) | 0.69 | 0 | 0.57
DRL (Compile/UT) | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:12 PM el 18/04/2017