## excel(14)
/Non Project/PSP Fundamentals & Advanced/Program 6
Size Estimating Template (instructions...)
The PROBE Wizard uses Estimated Proxy Size as the basis for generating final estimates for size and time. However, after you last ran the PROBE Wizard, you modified the estimates on this form, causing the Estimated Proxy Size to change. Your current PROBE estimates are based upon the old value of Estimated Proxy Size. To resolve this problem, you should double-check the values in the form below, then run the PROBE Wizard again.
Project Owner | Juvenal Alberto RiaÃ±o Heredia
Size Measure | LOC
BASE PARTS |  |  | Estimated |  |  |  |  | Actual
|  |  | BASE | DELETED | MODIFIED | ADDED |  | BASE | DELETED | MODIFIED | ADDED
Dato |  |  | 25 | 3 | 2 | 2 |  | 19 | 4 | 2 | 0
Controlador |  |  | 27 | 5 | 0 | 11 |  | 76 | 0 | 5 | 33
Calculo |  |  | 117 | 0 | 15 | 20 |  | 151 | 0 | 2 | 27
AdministrarDatos |  |  | 58 | 15 | 5 | 10 |  | 37 | 17 | 2 | 0
Vista |  |  | 18 | 11 | 0 | 25 |  | 29 | 0 | 0 | 11
add more rows for base parts... | Total: |  | 245 | 34 | 22 | 68 |  | 312 | 21 | 11 | 71
PARTS ADDITIONS |  |  | Estimated | [5 empty] | Actual
|  |  | TYPE | ITEMS | REL. SIZE | SIZE | NR |  | SIZE | ITEMS | NR
add more rows for parts additions... |  |  |  | Total: |  | 0 |  |  | 0
REUSED PARTS |  |  | Estimated |  | Actual
|  |  | SIZE |  | SIZE
|  |  | 0 |  | 0
add more rows for reused parts... | Total: |  | 0 |  | 0
TOTAL SIZE |  | Actual
SIZE
Actual Size of Finished Product: |  | 312
Instructions: During the planning phase, complete the "Estimated" columns in the form above, then use the PROBE Wizard to fill out the fields below.
|  |  | SIZE |  | TIME
Added Size (A): | A = BA + PA |  | 68
Estimated Proxy Size (E): | E = BA + PA + M |  | 90
Last Estimated Proxy Size: (The value used on the last run of the PROBE Wizard) |  |  | 90
PROBE estimating basis used: (A, B, C, or D) |  |  | C |  | C1
Correlation: (r2) |  |  | N/A |  | N/A
Regression Parameters: | B0 (size and time) |  | 0 |  | 0
Regression Parameters: | B1 (size and time) |  | 0.91 |  | 1.81
Projected Added and Modified Size (P): | P = B0size + B1size * E |  | 81.8
Estimated Total Size (T): | T = P + B - D - M + R |  | 271
Estimated Total New Reusable (NR): | (sum of NR items) |  | 0
Estimated Total Development Time: | Time = B0time + B1time * E |  |  |  | 0.11319
Prediction Range: | Range |  | N/A |  | N/A
Upper Prediction Interval: | UPI = P + Range |  | N/A |  | N/A
Lower Prediction Interval: | LPI = P - Range |  | N/A |  | N/A
Prediction Interval Percent: |  |  | N/A |  | N/A
View PROBE Report
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.